## thursday-23
Timestamp	Task Id	task Name	Task Description	defects
06:30:00 AM	1	Form Project	Create project description and tasklist
07:00:00 AM	2	Add components	Add Following libraries and components: React diagramming, Spotlight NodeJs REST server, Thingsboard Server, Postgres Database, raspberry Pi VM
08:00:00 AM	3	Build Docker compose	Create docker compose yaml file to deploy all components into local docker CM and verify proper startup.
09:00:00 AM	4	Test Running cluster	Verify that all operations are running as expected, create github repository
10:00:00 AM	5	build local k8s env	install minicube, kubectl,, etcd, compose to deploy docker-compose file to minikube
11:00:00 AM	6	build deployment descriptors	used Kompose to convert docker-compose files to kubernets resources files
11:30:00 AM	7	build deployment scripts	wrote helm chart
12:00:00 PM	8	build deployment scripts	wrote intitial terraform
12:30:00 PM	9	build deployment scripts	build deploy/undeploy scripts to test k8s resources files
01:00:00 PM	10	Finish minikube deployment – checkin	debugging k8s deployment, check in IaC codebase
02:00:00 PM	11	Clean up	added namespace isolation for all components, modified tb to use differnt image, modified init db to correct minor issue, (failed at) loading spotlight data for rest service support	the change removed an embedded postgres database but broke the login process for the db
04:00:00 PM	12	debugging instability in tb deployment	Defect prevention. Tb deployment breakage is definitely related to the change in container image selection for tb in task #11

## friday-24
Timestamp	Task Id	task Name	Task Description	results
06:00:00 AM	2.1	configure gcloud sdk	verify gcloud account configuration is proper, project exists
07:00:00 AM	2.2	manual setup GKE cluster	setup online cluster, configs and controls for deployment
08:00:00 AM	2.3	update terraform GKE	Update GKE account details, repo locatons, deployment names etc
09:00:00 AM	2.4	test GKE deployment	run terraform deployment, verify deployment, operations and funtionalitry.
10:00:00 AM	2.5	update repo	Push working branch to github with ability to push to GKE
10:30:00 AM	2.51	update readme	add devops instructions for each deployment type to readme section with dependency section
11:00:00 AM	2.6	image registry	select and implement an image registry to give a shared location to push docker images allowing for distributed deployment access to those image.	ghcr.io, images built and pushed by actions
12:00:00 PM	2.7	test prod deployment	test and verify public deployment in GKE from github action event.	image registry solved problems with images beig unavailable, still resolving a persistence problem with GKE
01:00:00 PM	2.8	update db contents	verify and correct database init loads to ensure APIs are returning data.	looks like the db is having some mount point problems in GKE
02:00:00 PM	2.9	update persistence	update k8s persistence definitions to not use local filesystem hostpaths
03:00:00 PM	2.101	update postgres persistance	Created configmap in effort to initdb and setup the database for thingsboard and my code
04:00:00 PM	2.11	update postgres persistence	Worked on persistence claim to resolve defect unique to GKE where the PV directory was not empty on creation preventing the database from starting	database is still having issues,will try to create extended docker image for db to include initdb.sh and seed data

## Saturday-25
Timestamp	Task Id	task Name	Task Description	defects
06:00:00 AM	3.1	new postgres image from dockerfile	build and test new dockerfle based extended postgres:12 image to include start files in docker entry point, fix github actions to build and upload db image
07:00:00 AM	3.2	cluster deploy	deleted cluster deployment, ran terraform and captured log for apply, deleted all disks in gconsole
08:00:00 AM	3.3	deployed kubernetes	deployed pods into k8s, db stuck in pending status	no resources deployed, retrying again
09:00:00 AM	3.4	debug db startup	update repo, pshed devops changes, ran local db postgres and tested setup.
10:00:00 AM	3.5	resolv db init problems	fixed database initialization, creating the thingsboard database, users etc at startup of the container.	still having persistence issues in GKE, database files are ephemeral
11:00:00 AM	3.6	debug thingsboard startup problems.	now db is setup properly but tb is not starting correctly. Hibernate appears to fail in creating the schema etc.	modified deployment script to use default k8s env variables for DB server ip and port
12:00:00 PM	3.7	expose Uis to public IP address	successfully exposed UIs on port 9090, 8080 and 3000 creating load-balancer services
02:00:00 PM	3.8	add pi emulator container/add registration pi	update startup scripts for pi vm to call to the tb restful api instance and register the vm as a device for a tenant,
03:00:00 PM	3.9	Manually register fake pi device	call curl and register a device via json and REST in tb	generated the script based on the REST endpoint but have not executed it yet.
04:00:00 PM	3.101	automate previous steps in script	Create a script that registers an emulated device in the tb REST Api and returns device id
04:00:00 PM	3.11	Improve pi emulated image	added extended pi image to github actions and pushed to ghcr.io
05:00:00 PM	3.12	Build k8s deploy for pi	build resource yaml for k8s deployment of pi image using registry image id
06:00:00 PM	3.13	updated README, tasks and docs.	updated readme contents and details. Still working on spreadsheet conversion.

## Sunday-26
Timestamp	Task Id	task Name	Task Description
06:00:00 AM	4.1
07:00:00 AM	4.2
08:00:00 AM	4.3
09:00:00 AM	4.4
10:00:00 AM	4.5
11:00:00 AM	4.60000000000001
12:00:00 PM	4.70000000000001
01:00:00 PM	4.80000000000001
02:00:00 PM	4.90000000000001
03:00:00 PM	4.101
04:00:00 PM	4.11
05:00:00 PM	4.12
06:00:00 PM	4.13